## Month 1
Job Tracking Template
Visit Thryv.com to Learn More
Job ID # | Customer's Name | Contact Information | Job Address | Job Type | Job Description | Team Members Assigned to the Job | Materials | Estimated Cost | Actual Cost | Start Date | Projected End Date | Actual Completion Date | Job Status | Notes | Amount Billed to Customer | Invoice Number | Payment Due Date | Payment Status | Payment Notes | Net Profit
123 | Sarah Thompson | Email: sarah.thompson@email.com Phone: (561) 555-0192 | 123 Palm Breeze Dr, Stuart, FL 34997 | Residential Electrical Installation | Install wiring and outlets for a new kitchen remodel, including GFCI protection. | Mike R. Jenna T. | 12-gauge wire, GFCI outlets, junction boxes, wall plates | 2400 | 2200 | 2025-08-10 | 2025-08-12 | 2025-08-13 | Completed | Added extra outlet per customer request. | 2650 | INV-005 | 2025-08-20 | Invoice Paid | Paid in full via credit card. | 450 | Total Jobs Completed: | 4
124 | Coastal Café | Email: manager@coastalcafe.com Phone: (772) 555-8832 | 456 Oceanview Blvd, Stuart, FL 34996 | Commercial Electrical Installation | Install new circuits and lighting for café expansion. | David Brown Lenny Carter Tom Harris | Commercial-grade conduit, LED fixtures, breakers, wiring | 5800 | 5300 | 2025-08-01 | 2025-08-07 | 2025-08-06 | Completed | Completed ahead of schedule. | 5800 | INV-006 | 2025-08-15 | Invoice Paid | Paid via bank transfer. | 500 | Total Revenue: | 12400
125 | James & Linda Carter | Email: carter.family@email.com Phone: (772) 555-1122 | 789 Sunset Ln, Stuart, FL 34994 | Emergency Services | Emergency repair of shorted circuit causing power outage in living room. | Eric D. Mark W. | Replacement breaker, outlet, wire nuts | 450 | 400 | 2025-08-24 | 2025-08-24 | 2025-08-24 | Completed | Replaced damaged breaker and rewired outlet. | 450 | INV-007 | 2025-09-01 | Invoice Sent | Awaiting payment. | 50 | Total Costs: | 10900
126 | GreenTech Solutions | Email: support@greentech.com Phone: (561) 555-7788 | 321 Innovation Way, Stuart, FL 34997 | Panel Upgrades & Circuit Additions | Upgrade electrical panel to 200 amps and add dedicated circuits for new equipment. | Sean T. James W. | 200A panel, breakers, copper wire, conduit | 3200 | 3000 | 2025-08-20 | 2025-08-25 |  | In Progress | Waiting on delivery of upgraded panel. | 3500 | INV-008 |  | Invoice Not Paid |  | 500 | Total Net Profit: | 1500
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0