## Month 1
Job Tracking Template
Visit Thryv.com to Learn More
Job ID # | Customer's Name | Contact Information | Job Address | Job Type | Job Description | Team Members Assigned to the Job | Materials | Estimated Cost | Actual Cost | Start Date | Projected End Date | Actual Completion Date | Job Status | Notes | Amount Billed to Customer | Invoice Number | Payment Due Date | Payment Status | Payment Notes | Net Profit
123 | John Smith | Email: john.smith@example.com Phone: (555) 123-4567 | 123 Maple Street, Springfield, IL 62701 | HVAC Repair | Repair malfunctioning HVAC system to restore optimal heating and cooling. | Alex Johnson Mario Lopez | - Replacement parts (e.g., capacitors, motors) - Refrigerant - HVAC tools (e.g., gauges, wrenches) - Air filters | 550 | 500 | 2025-03-01 | 2025-03-03 | 2025-03-04 | Completed | Replaced faulty capacitor and recharged refrigerant. | 660 | INV-005 | 2025-03-05 | Invoice Paid | Paid in full via credit card. | 160 | Total Jobs Completed: | 4
124 | Eleanor Fields | Email: eleanor.fields@example.com Phone: (555) 234-5678 | 456 Oak Avenue, Springfield, IL 62702 | HVAC Installation or Replacement | Install new HVAC system to improve energy efficiency and indoor comfort. | David Brown Lenny Carter Tom Harris | - HVAC unit (e.g., furnace, air conditioner) - Ductwork - Thermostat - Insulation | 4200 | 4000 | 2025-04-05 | 2025-04-07 |  | In Progress | Installed new energy-efficient HVAC system. | 5040 | INV-006 | 2025-04-12 | Invoice Sent | Invoice sent. | 1040 | Total Revenue: | 6984
125 | Michael Jones | Email: michael.jones@example.com Phone: (555) 345-6789 | 789 Pine Road, Springfield, IL 62703 | Emergency Services, HVAC Repair | Provide emergency HVAC service to address urgent heating and cooling issues. | Eric Davis Mark Wilson | - Emergency repair kit - Replacement parts - Refrigerant - HVAC tools | 750 | 700 | 2025-03-15 | 2025-03-16 | 2025-03-16 | Completed | Emergency repair completed to restore heating. | 900 | INV-007 | 2025-03-17 | Invoice Paid | Paid in full via cash. | 200 | Total Costs: | 5500
126 | Sally Brown | Email: sally.brown@example.com Phone: (555) 456-7890 | 101 Birch Lane, Springfield, IL 62704 | Duct Cleaning | Clean and sanitize ductwork to improve indoor air quality and system efficiency. | Sean Thompson James White | - Duct cleaning equipment (e.g., brushes, vacuums) - Sanitizing agents - Air filters - Protective gear | 400 | 300 | 2025-04-06 | 2025-04-06 |  | Not Started | Ducts cleaned and sanitized to improve air quality. | 384 | INV-008 | 2025-04-08 | Invoice Sent | Invoice sent. | 84 | Total Net Profit: | 1484
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0