## Month 1
Job Tracking Template
Visit Thryv.com to Learn More
Job ID # | Customer's Name | Contact Information | Job Address | Job Type | Job Description | Team Members Assigned to the Job | Materials | Estimated Cost | Actual Cost | Start Date | Projected End Date | Actual Completion Date | Job Status | Notes | Amount Billed to Customer | Invoice Number | Payment Due Date | Payment Status | Payment Notes | Net Profit
123 | John Smith | Email: john.smith@example.com Phone: (555) 123-4567 | 123 Maple Street, Springfield, IL 62701 | Landscape Design, Landscape Installation, Irrigation Systems | Design and install a new landscape with an efficient irrigation system. | Alex Johnson Mario Lopez | - Plants and shrubs - Irrigation pipes and sprinklers - Soil and mulch - Landscape fabric | 3200 | 2900 | 2025-04-01 | 2025-04-15 | 2025-04-15 | Completed | Installed a beautiful landscape with a state-of-the-art irrigation system. | 4000 | INV-001 | 2025-04-17 | Invoice Sent | Invoice sent. | 1100 | Total Jobs Completed: | 4
124 | Eleanor Fields | Email: eleanor.fields@example.com Phone: (555) 234-5678 | 456 Oak Avenue, Springfield, IL 62702 | Hardscaping, Mulching and Edging, Seasonal Cleanups | Install hardscaping features, mulch and edge garden beds, and perform seasonal cleaning. | David Brown Lenny Carter Tom Harris | - Pavers and stones - Mulch - Edging materials - Cleaning tools | 2600 | 2000 | 2025-04-05 | 2025-04-07 | 2025-04-08 | Completed | Enhanced the garden with hardscaping and fresh mulch, and cleaned up for the season. | 3375 | INV-002 | 2025-04-09 | Invoice Paid | Paid in full via bank transfer. | 1375 | Total Revenue: | 13775
125 | Michael Jones | Email: michael.jones@example.com Phone: (555) 345-6789 | 789 Pine Road, Springfield, IL 62703 | Pest and Weed Control, Landscape Maintenance, Seasonal Cleanups | Provide pest and weed control, regular maintenance, and seasonal cleaning. | Eric Davis Mark Wilson | - Pest control products - Weed control products - Maintenance tools - Cleaning supplies | 1200 | 975 | 2025-04-12 | 2025-04-12 | 2025-04-12 | In Progress | Created a pest-free and well-maintained garden, ready for the new season. | 1600 | INV-003 | 2025-04-13 | Invoice Sent | Invoice sent. | 625 | Total Costs: | 9075
126 | Sally Brown | Email: sally.brown@example.com Phone: (555) 456-7890 | 101 Birch Lane, Springfield, IL 62704 | Landscape Design, Landscape Installation, Landscape Maintenance | Design and install a new landscape, and provide ongoing maintenance. | Sean Thompson James White | - Plants and shrubs - Soil and mulch - Maintenance tools - Fertilizers | 3700 | 3200 | 2025-04-25 | 2025-04-26 | 2025-04-26 | Not Started | Creating a stunning landscape and set up a maintenance plan to keep it looking great. | 4800 | INV-004 | 2025-04-27 | Invoice Not Paid | Invoice not sent yet. | 1600 | Total Net Profit: | 4700
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0