## Month 1
Job Tracking Template
Visit Thryv.com to Learn More
Job ID # | Customer's Name | Contact Information | Job Address | Job Type | Job Description | Team Members Assigned to the Job | Materials | Estimated Cost | Actual Cost | Start Date | Projected End Date | Actual Completion Date | Job Status | Notes | Amount Billed to Customer | Invoice Number | Payment Due Date | Payment Status | Payment Notes | Net Profit
123 | John Smith | Email: john.smith@example.com Phone: (555) 123-4567 | 123 Maple Street, Springfield, IL 62701 | Plumbing Repair | Repair leaking pipes and fixtures to prevent water damage. | Alex Johnson Mario Lopez | - Pipe fittings - Plumber's tape - Wrenches - Sealant | 450 | 400 | 2025-03-01 | 2025-03-02 | 2025-03-02 | Completed | Replaced damaged pipes and fixed leaking faucet. | 560 | INV-001 | 2025-03-03 | Invoice Paid | Paid in full via credit card. | 160 | Total Jobs Completed: | 4
124 | Eleanor Fields | Email: eleanor.fields@example.com Phone: (555) 234-5678 | 456 Oak Avenue, Springfield, IL 62702 | Water Heater Services | Service and repair water heater to ensure efficient operation. | David Brown Lenny Carter Tom Harris | - Replacement parts (heating elements, thermostat) - Pipe insulation - Wrenches - Plumber's tape | 650 | 575 | 2025-03-05 | 2025-03-05 | 2025-03-05 | Completed | Replaced faulty heating element and insulated pipes. | 815 | INV-002 | 2025-03-06 | Invoice Paid | Paid in full via bank transfer. | 240 | Total Revenue: | 2565
125 | Michael Jones | Email: michael.jones@example.com Phone: (555) 345-6789 | 789 Pine Road, Springfield, IL 62703 | Emergency Services, Leak Detection | Emergency plumbing service to address severe leak. | Eric Davis Mark Wilson | - Emergency repair kit - Pipe fittings - Sealant - Wrenches | 575 | 500 | 2025-03-16 | 2025-03-16 |  | In Progress | Emergency repair completed to stop severe leak. | 715 | INV-003 | 2025-03-17 | Invoice Sent | Invoice sent. | 215 | Total Costs: | 1775
126 | Sally Brown | Email: sally.brown@example.com Phone: (555) 456-7890 | 101 Birch Lane, Springfield, IL 62704 | Drain Cleaning | Clean and unclog drains to ensure proper water flow. | Sean Thompson James White | - Drain snake - Plunger - Drain cleaning solution - Protective gloves | 400 | 300 | 2025-03-10 | 2025-03-10 | 2025-03-10 | Not Started | Cleared major clog and cleaned drains thoroughly. | 475 | INV-004 | 2025-03-10 | Invoice Sent | Invoice sent. | 175 | Total Net Profit: | 790
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0