## Month 1
Job Tracking Template
Visit Thryv.com to Learn More
Job ID # | Customer's Name | Contact Information | Job Address | Job Type | Job Description | Team Members Assigned to the Job | Materials | Estimated Cost | Actual Cost | Start Date | Projected End Date | Actual Completion Date | Job Status | Notes | Amount Billed to Customer | Invoice Number | Payment Due Date | Payment Status | Payment Notes | Net Profit
123 | John Smith | Email: john.smith@example.com Phone: (555) 123-4567 | 123 Maple Street, Springfield, IL 62701 | Roof Repair, Gutter Repair | Repair roof and gutters to address leaks and ensure proper drainage. | Alex Johnson Mario Lopez | - Roofing shingles - Gutter sealant - Roofing nails - Flashing | 1200 | 1350 | 2025-03-01 | 2025-03-10 | 2025-03-12 | Completed | Extra time needed to address unexpected gutter issues. | 1800 | INV-001 | 2025-03-12 | Invoice Paid | Paid in full via credit card. | 450 | Total Jobs Completed: | 4
124 | Eleanor Fields | Email: eleanor.fields@example.com Phone: (555) 234-5678 | 456 Oak Avenue, Springfield, IL 62702 | Roof Replacement | Replace entire roof with new, durable materials. | David Brown Lenny Carter Tom Harris | - Asphalt shingles - Underlayment - Roofing nails - Ridge vents | 5000 | 4800 | 2025-04-05 | 2025-04-20 |  | Not Started | Roof replacement completed projected to be on schedule. | 6500 | INV-002 | 2025-04-05 | Invoice Paid | Paid in full via bank transfer. | 1700 | Total Revenue: | 10500
125 | Michael Jones | Email: michael.jones@example.com Phone: (555) 345-6789 | 789 Pine Road, Springfield, IL 62703 | Gutter Installation | Install new gutters to improve water management and protect the foundation. | Eric Davis Mark Wilson | - Gutters - Downspouts - Gutter hangers - Gutter guards | 800 | 850 | 2025-03-31 | 2025-04-07 |  | In Progress | Installation delayed due to weather conditions. | 1200 | INV-003 | 2025-04-07 | Invoice Sent | Invoice not paid yet. | 350 | Total Costs: | 7650
126 | Sally Brown | Email: sally.brown@example.com Phone: (555) 456-7890 | 101 Birch Lane, Springfield, IL 62704 | Emergency Services, Roof Repair | Perform emergency roof repair to fix severe damage and prevent further issues. | Sean Thompson James White | - Tarp - Roofing cement - Roofing nails - Plywood sheets | 600 | 650 | 2025-03-15 | 2025-03-16 | 2025-03-16 | Completed | Emergency repair successfully completed within 24 hours. | 1000 | INV-004 | 2025-03-16 | Invoice Paid | Paid in full via cash. | 350 | Total Net Profit: | 2850
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0